# Example: the general proposal filled in

Replace every [bracket] and every example figure with your own scope, dates and prices, and delete this note before sending. A proposal describes the offer; attach a services agreement that covers ownership, confidentiality, liability, cancellation and governing law before work starts.

Source: https://agencypro.app/proposals#general-proposal-example

# AGENCY SERVICES PROPOSAL

Prepared for: Operations Director, [Client], a 40-person B2B software company (example)

Prepared by: [Agency], account lead [Name]

Date and validity: [Date]; valid for 30 days

# 1. Summary

Demo requests from the website have been flat for two quarters while traffic grew, and the sales team cannot see which pages lead to demos.

Proposed solution: rebuild the five highest-traffic service pages and the demo form, and set up conversion tracking so every demo request is attributed to a page.

Expected outcome: a measurable demo conversion rate per page within 30 days of launch, against the baseline we record in week 1.

Investment: $18,000 fixed fee in three payments (example figure).

Next step: approve the scope by [date] so discovery can start on [date].

# 2. Your goal and current situation

Goal: more demo requests from existing traffic. Baseline: [demo requests per month and site sessions from your analytics, recorded in week 1].

Assumption to confirm: the CRM can receive form submissions with a source field.

What happens if nothing changes: paid and organic traffic keeps growing without a matching rise in demos.

# 3. Proposed approach

Phase 1, discovery (weeks 1-2): 4 stakeholder interviews, analytics review, page and form audit.

Phase 2, design (weeks 3-5): wireframes and designs for 5 pages and the demo form.

Phase 3, build and tracking (weeks 6-8): build in the current CMS; form-to-CRM connection; conversion events.

Risks and how we manage them: content approvals slip; we agree one approver and a 3-working-day review window.

# 4. Scope and deliverables

Discovery summary (PDF; acceptance: approved by the Operations Director).

5 page designs and 1 form design (Figma; 2 revision rounds each).

5 built pages and 1 form on staging, then production (acceptance: QA checklist passes on the named browsers).

Tracking plan and conversion events (acceptance: test submissions appear in analytics and the CRM).

Optional add-on: copywriting for the 5 pages, $3,000 (example figure).

Not included: new pages beyond the 5, paid media, CRM configuration beyond the form connection.

# 5. Timeline and responsibilities

Week 2: discovery summary approved (client: interview availability by week 1).

Week 5: designs approved (client: feedback within 3 working days per round).

Week 8: launch (client: final copy by week 6).

Client approver: Operations Director.

# 6. Investment

$18,000 fixed: $7,200 on signing, $5,400 on design approval, $5,400 at launch (example figures). Hosting and software licences stay on your accounts.

Additional work: quoted and approved in writing before it starts.

# 7. Reporting and communication

Weekly status email every Friday; shared project board; escalation to [Agency director].

# 8. Team and relevant experience

Team: account lead, designer, developer, analytics specialist.

Experience: [Add real, permissioned examples only.]

# 9. Next steps

Confirm the approver, approve this scope, sign the services agreement and pay the first invoice. Discovery starts the following Monday.